## Branding Tracker
PET CAFÉ — BRANDING TRACKER ¦ 14–16 Weeks ¦ ₹14,50,000 + GST
Stage | Deliverable | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16
Stage 1 Creative Research & Brand Idea | Creative Research
Category brands: in the consumer's consideration set
Inspiration brands
Research on visual & verbal cues
Consumer Understanding | bar: Wk 1 to Wk 5
Behaviours and motivations to visit a pet cafe and grooming center,One-on-one qualitative in-depth interviews with 10 consumers informally recruited through Please See & client's network | bar: Wk 1 to Wk 5
Creative Idea | bar: Wk 1 to Wk 5
Building the central idea for the Pet cafe
Stage 2 Brand Transformation | Brand identity | bar: Wk 6 to Wk 8
Logo | bar: Wk 6 to Wk 8
Mnemonic | bar: Wk 6 to Wk 8
Visual Language | bar: Wk 1 to Wk 2; Wk 5 to Wk 8; Wk 10 to Wk 16
Typography | bar: Wk 6 to Wk 8
Illustration style/Iconography style (only setup) | bar: Wk 1 to Wk 2; Wk 5 to Wk 8; Wk 10 to Wk 16
Photography Style | bar: Wk 6 to Wk 8
Verbal Language | bar: Wk 1 to Wk 2; Wk 5 to Wk 8; Wk 10 to Wk 16
Brand story (consumer facing story) | bar: Wk 6 to Wk 8
Tone of Voice | bar: Wk 1 to Wk 2; Wk 5 to Wk 8; Wk 10 to Wk 16
Stage 3 Brand Collaterals | Facade Design x2*
Signage x2 | bar: Wk 1 to Wk 4; Wk 7 to Wk 13; Wk 16
Window decals x2
Regional Logo x2 | bar: Wk 1 to Wk 4; Wk 7 to Wk 13; Wk 16
In-store Signage Template x2
In-store Posters/Graphics Template x2 | bar: Wk 1 to Wk 4; Wk 7 to Wk 13; Wk 16
All visuals and verbal communication (fleshed out for 2 posters) | bar: Wk 1 to Wk 4; Wk 7 to Wk 13; Wk 16
Set up for extendability (template to carry forward) | bar: Wk 1 to Wk 4; Wk 7 to Wk 13; Wk 16
Menu x2
Food x1 | bar: Wk 1 to Wk 4; Wk 7 to Wk 13; Wk 16
Grooming Services x1
Includes:Format recommendations (one pager, board, folded card etc)
Print specs recommendations
Cover design
Menu layout
Print ready artwork files
Staff Uniform design recommendation x2
T-shirt
Apron
Table call outs, napkins and coasters x3
Bill Folder for x1
Take away collaterals x3
Bag design
Cups
Boxes
Stage 4 Brand Guidelines | Brand centre
Logo-usage | bar: Wk 14 to Wk 15
Type-usage
Colours usage and proportions
Illustration style setup-Usage and Proportions | bar: Wk 14 to Wk 15
Tone of Voice | bar: Wk 14 to Wk 15
Usage of graphic assets across packaging/ communication (where applicable) | bar: Wk 14 to Wk 15
Imagery-Style guide for usage | bar: Wk 14 to Wk 15
■ Stage 1 — Creative Research & Brand Idea ■ Stage 2 — Brand Transformation ■ Stage 3 — Brand Collaterals ■ Stage 4 — Brand Guidelines
*=Only design and material suggestions, No fabrication

## Comments , feedback and updates
PET CAFÉ — BRANDING TRACKER ¦ 14–16 Weeks Duration
Stage | Deliverable | Received on | Please See - Member 1 (Deliverables provided by) | Fetch - Member 1 (Check - Date) | Fetch - Member 1 Comments | Fetch - Member 2 Comments | Feedback Shared (Date) | Revised update (Date) | Drive Link
Stage 1 Creative Research & Brand Idea | Creative Research
Category brands: in the consumer's consideration set
Inspiration brands
Research on visual & verbal cues
Consumer Understanding
Behaviours and motivations to visit a pet cafe and grooming center,One-on-one qualitative in-depth interviews with 10 consumers informally recruited through Please See & client's network
Creative Idea
Building the central idea for the Pet cafe
Stage 2 Brand Transformation | Brand identity
Logo
Mnemonic
Visual Language
Typography
Illustration style/Iconography style (only setup)
Photography Style
Verbal Language
Brand story (consumer facing story)
Tone of Voice
Stage 3 Brand Collaterals | Facade Design x2*
Signage x2
Window decals x2
Regional Logo x2
In-store Signage Template x2
In-store Posters/Graphics Template x2
All visuals and verbal communication (fleshed out for 2 posters)
Set up for extendability (template to carry forward)
Menu x2
Food x1
Grooming Services x1
Includes:Format recommendations (one pager, board, folded card etc)
Print specs recommendations
Cover design
Menu layout
Print ready artwork files
Staff Uniform design recommendation x2
T-shirt
Apron
Table call outs, napkins and coasters x3
Bill Folder for x1
Take away collaterals x3
Bag design
Cups
Boxes
Stage 4 Brand Guidelines | Brand centre
Logo-usage
Type-usage
Colours usage and proportions
Illustration style setup-Usage and Proportions
Tone of Voice
Usage of graphic assets across packaging/ communication (where applicable)
Imagery-Style guide for usage